## Completed_task
Task ID | Task Description | Status | Completed By | Verified By | Completion Date | Remarks
1 | Wiremock screens design for all webpages | Completed | Pari | Soo-yeon | Aug
2 | Project setup | Completed | Pari | Soo-yeon | Aug
3 | Created static UI and layout design for all pages (Overview, Home, Networks, Countries, States). | Completed | Pari | Soo-yeon | Sept
4 | Integrated data to make it dynamic (Overview, Home, Networks, Countries) pages. | Completed | Pari |  | 2025-10-10
5 | Help and guide page UI static page | Completed | Hidhayathnisha |  | 2025-10-12
| States page data integration | Completed | Hidhayathnisha |  | 2025-10-12

## Bugs_to_fix
Overview
Bug ID | Description | Status | Completed By | Identified By | Remarks
Home
Map
Bug ID | Description | Status | Completed By |  | Remarks
1 | Maps should be updated to WorldMap 2 |  |  | pari
2 | Data integration with filters |  |  | pari
3 | Fix version button |  |  | pari
Percent Change
Bug ID | Description | Status | Completed By |  | Remarks
1 | Maps should be updated to WorldMap 2 |  |  | pari
2 | Data integration with filters |  |  | pari
3 | Fix version button |  |  | pari
Data & Download (Cookbook)
Bug ID | Description | Status | Completed By |  | Remarks
1 | ID and variable dropdowns values should be added to filter the data. Check with Soo for the filtration logic. |  |  | pari
About
Bug ID | Description | Status | Completed By |  | Remarks
1 | Get content from Soo-Yeon |  |  | pari
Countries
Bug ID | Description | Status | Completed By |  | Remarks
1 | Fix the map with the latest design |  |  | pari
Networks
Bug ID | Description | Status | Completed By |  | Remarks
1 | Fix the data version button UI |  |  | pari
2 | Update the membership dropdown with the right data |  |  | pari
3 | Fix page load delay
States
Bug ID | Description | Status | Completed By |  | Remarks
1 | Fix the graphs — both time-series misalignments and labeling issues |  |  | pari
2 | Update to the latest map |  |  | pari
Help & Guide
Bug ID | Description | Status | Completed By |  | Remarks
1 | Video placeholder is not added — it should be added |  |  | pari